BEFORE

THE PUBLIC UTILITIES COMMISSION OF OHIO

| In the Matter of the Commission’s Review of Ohio Power Company’s Distribution Investment Rider Plan. | : : | Case No. 12-3129-EL-UNC |
| --- | --- | --- |

________________________________________________________________________

COMMENTS ON OHIO POWER’S DIR WORK PLAN

SUBMITTED ON BEHALF OF THE STAFF OF

THE PUBLIC UTILITIES COMMISSION OF OHIO

______________________________________________________________________

Michael DeWine

Ohio Attorney General

William L. Wright

Section Chief

Werner L. Margard

Assistant Attorney General

Public Utilities Section

180 East Broad Street, 6th Fl.

Columbus, OH  43215

614.466.4395 (telephone)

614.644.8764 (fax)

werner.margard@puc.state.oh.us

Background and Purpose

In its August 8, 2012 Opinion and Order (O&O) in Case No.11-346-EL-SSO, the Commission approved, with certain modifications, the Distribution Investment Rider (DIR) proposed  by Columbus Southern Power Company and Ohio Power Company, which were subsequently merged to form a combined Ohio Power Company (OP or Company).  On Page 47 of that O&O, the Commission directed the Company to:

“. . . work with Staff to develop a plan to emphasize proactive distribution maintenance that focuses on spending where it will have the greatest impact on maintaining and improving reliability for customers . . .” and to “file the plan for Commission review in a separate docket . . .”

On December 3, 2012, OP filed its DIR Work Plan for 2013 (the Plan) in the instant case.  Subsequently the attorney examiner issued a procedural entry requiring Staff and intervenors to file any comments on the DIR Work Plan by January 18, 2013.  The remainder of this document comprises Staff’s comments on the Plan.

The two-fold purpose of these comments is:  (1) to describe how the Company worked with Staff to develop the Plan; and (2) to describe Staff’s expectations for the Plan and for the Company’s future actions regarding this Plan for 2013 as well as the subsequent DIR plan for year 2014.

1.	Ohio Power Company (OP) did work with Staff to develop the DIR Work Plan.

That collaborative effort included the following chronological steps:

(a)	Staff analyzed the Company’s historical outage-by-cause data to identify the primary controllable outage causes;

(b)	The Company provided Staff a list of all DIR-related distribution capital programs proposed for year 2013, and for each program a listing of equipment to be replaced.  For those programs that OP expected to improve or maintain reliability, the Company also explained how those programs were expected to bring about such reliability improvement;

(c)	Staff used the results of its analysis in Step (a) to rank each proposed program.;

(d)	The Company provided Staff its projected capital expenditures for each of the listed programs; and

(e)	Staff evaluated the Company’s projected expenditures for each program.

Based on the results of the above process, the Staff expects the majority of programs listed in the DIR Work Plan to either maintain, improve, or have no impact on reliability in the localities where they are implemented.  More broadly, Staff also expects that the combined impact of these programs will result in improved reliability performance across the Company’s entire service territory.  Whether that broader expectation is achieved will depend on the level of expenditures for those programs that improve or maintain reliability.  At this time, Staff does not know whether the planned expenditure levels for those programs are sufficient to achieve this goal.  Staff, therefore, will monitor OP’s implementation of the programs as well as any improvements in OP’s overall reliability.

2.	Staff expects OP to provide periodic updates in 2013 on its progress implementing the DIR Work Plan.

Beginning in 2013, Staff expects OP to provide quarterly status reports not only on overall Plan implementation but also on each capital program in the Plan.  OP should provide each quarterly status report in writing.  Each status report should include:

(a)	For each program, a statement of year- to-date expenditures, both as a dollar amount and as a percentage of the planned total for 2013, and a comparison of that percentage against the percentage of the year completed to date, with an explanation for any variances exceeding ten percent;

(b)	For each program, a quantification of activities  or work units completed year- to-date, both as a numerical quantity and as a percentage of the total planned for 2013, and a comparison of that percentage against the percentage of the year completed to date, with an explanation for any variances exceeding ten percent;

(c)	For the Plan as a whole, a statement of year- to-date expenditures, both as a dollar amount and as a percentage of the total planned for 2013, and a comparison of that percentage against the percentage of the year completed-to-date, with an explanation for a variance of more than ten percent

In addition to the above-described quarterly reporting, OP is also expected to keep Staff informed about ongoing program-specific construction activities so Staff can perform field verification of facility installations as they occur.

3.	Staff expects OP to work with Staff in the fourth quarter of 2013 to develop the 2014 Work Plan.

Since the Plan OP filed on December 3, 2012 addresses only 2013 capital expenditures, OP will need to work with Staff again in 2013 to develop the 2014 DIR Work Plan for the final year of its Electric Security Plan (ESP).  Staff expects this process to proceed according to the following schedule:

(a)	By October 1, 2013, OP should provide Staff an update of its historical outage-by-cause data at the same level of detail that OP provided in 2012.

(b)	By October 15, 2013, OP should provide Staff a list of all DIR-related distribution capital programs proposed for 2014 and for each program a listing of equipment to be replaced.  For each program that OP expects to maintain or improve reliability, the Company should include an explanation of how the program will bring about such a result.

(c)	By November 1, 2013, Staff will provide OP a ranking of programs based on Staff’s ratings of relative importance.  These ratings will be guided by the results of Staff’s analysis of OP’s historical outage-by-cause data.

(d)	By November 15, OP should provide Staff its projected expenditures and associated activities/work units for each program.

(e)	By December 15, OP should file its 2014 DIR Work Plan.

4.	Staff expects OP to quantify actual reliability improvements achieved for those programs that are expected to reduce the frequency and/or duration of outages.

After OP has implemented the 2013 DIR Work Plan, Staff expects OP to quantify the reliability impact (in terms of reduced outage frequency and/or duration) of each program that was expected to improve reliability.  For each program that was expected to maintain (instead of improve) reliability, Staff expects OP to quantify the outages avoided by implementing the program in 2013.  OP should provide Staff this information in writing by February 28, 2014.

5.	Staff expects OP to reflect the impact of DIR implementation in more stringent future reliability standards.

Since the Commission has granted OP accelerated recovery of its DIR costs, and since these costs are expected to improve reliability, Staff believes such reliability improvements should be reflected in more stringent OP reliability standards in the future.  Consistent with this belief, Staff has recommended, in Case No. 12-1945-EL-ESS, that OP file an application for new reliability standards in year 2016.  Such new standards should reflect the impact on reliability of not only the Rider DIR expenditures, but also that of the ESR Rider (vegetation management expenditures) and the gridSMART Rider (distribution automation expenditures).

Conclusion

Staff respectfully requests the Commission adopt the recommendations above.

Respectfully Submitted,

Michael DeWine

Ohio Attorney General

William L. Wright

Section Chief

/s/ Werner L. Margard

Werner L. Margard

Assistant Attorney General

Public Utilities Section

180 East Broad Street, 6th Fl.

Columbus, OH  43215

614.466.4395 (telephone)

werner.margard@puc.state.oh.us

- CERTIFICATE OF SERVICE

I hereby certify that a true copy of the foregoing Comments submitted on behalf of the Staff of the Public Utilities Commission of Ohio was served by electronic mail upon the following parties of record, this 18th day of January, 2013.

/s/ Werner L. Margard

Werner L. Margard

Assistant Attorney General

PARTIES OF RECORD:

Steven T. Nourse

Matthew J. Satterwhite

American Electric Power Corporation

1 Riverside Plaza, 29th Floor

Columbus, Ohio 43215-2373

stnourse@aep.com

mjsatterwhite@aep.com

Mark S. Yurick

Zachary D. Kravitz

Taft Stettinius & Hollister LLP

65 East State Street, Suite 1000

Columbus, Ohio 43215

myurick@taftlaw.com

zkravitz@taftlaw.com

Attorneys for The Kroger Co.